## Slide 1: Expectations for ITER in the 2020’s
T.C. Luce
Director, Science and Operations Department
Chief Scientist
ITER Organization

## Slide 2: The 2020’s Will See ITER Come to Life
To use an obvious cliché, we have ‘great’ expectations for the ITER Project in the 2020’s
Some high points:
  2020: Begin tokamak assembly; begin cryoplant commissioning
  2022: Torus completion
  2024: Cryostat closure
  2025: First Plasma
  2026: Begin installation of in-vessel components
  2028: Begin commissioning of control and protection systems with plasma operation up to 7.5 MA (maybe 10 MA)

## Slide 3: Roadmap for this Talk
Present highlights of the plans for:
  Component fabrication
  Site construction and assembly
  System commissioning
  Research program
… using present status as an indicator of the progress in maintaining the schedule

## Slide 4: Who manufactures what? The ITER Members share all intellectual property
Toroidal Field coils (18)
Poloidal field coils (6)
Cryostat
Thermal shield
Vacuum vessel
Blanket modules
Feeders (31)
Divertor
Central solenoid (6)
Correction coils (18)

## Slide 5
Major Component Fabrication Milestones
Key components begin to arrive in 2019:
TF coils
CS coils
PF coils
VV sectors
Cryostat (base/lower cylinder on site now)

## Slide 6
    70 Double Pancakes (DP) to build:
    Winding of 70 DP completed 100%
    70 Radial Plates completed 100%
    H.T and insertion of 70 DPs completed 100%
    Cover plates welding of 70 DPs completed 100%
    65 DPs impregnated & completed  93%
Manufacturing of Winding Packs for Toroidal Field Coils
EU
    10 Winding Packs (WP) to build:
    Stacking of 8 WPs completed 80%
    Ground insulation of 7 WPs completed 70%
    VPI of 5 WPs completed 50%
    Final assembly & test of 4 WPs completed 40%
    Delivery of 3 WPs completed 30%
Production optimized to match the delivery of TFCS by JA-DA (to avoid expensive storage of WPs)
5th WP after VPI. Ready for final assembly.
6th WP preparation prior to VPI

## Slide 7
Insertion of Winding Pack (WP) into Coil Cases for Toroidal Field Coils
EU
Assembly rigs tested with 1st TF Coil Case – insertion dry run
3 WPs at SIMIC premises:
1st cold tested and ready for insertion.
2nd cold tested and preparation for insertion ongoing.
3rd preliminary test before cold test starting imminently.
2 TF Coil Cases delivered by JA-DA at SIMIC premises:
1st released for Insertion.
2nd acceptance tests on-going.

## Slide 8: TF Coil Winding Pack (WP), Cold Test Started
The first winding pack (WP) has been installed inside Cryostat for its cold test at 80K. The cold tests are in progress at Mitsubishi Electric Corporation in Futami. The winding pack is to be inserted into TF coil structures to form TF Coil #12.
Status of TF Coil Winding
1st winding pack:
The cold test ongoing.
2nd winding pack:
Impregnation completed, and cooling pipe assembly ongoing.
3rd winding pack:
Double pancake (DP) stacking, WP insulation, joint between DPs completed. WP impregnation ongoing.
4th, 5th winding packs:
Cover plate (CP) welding, DP insulation, DP impregnation ongoing.
6th winding pack:
Radial plate fabrication, transfer, conductor insulation and CP welding ongoing.

## Slide 9: 5 of 7 Central Solenoid Modules in Fabrication
Work stations at General Atomics, from left: Preparation for vacuum pressure impregnation, post-heat treatment, ground insulation, and turn insulation.
A sleeve is placed over Module 1 in preparation for vacuum pressure impregnation.

## Slide 10
Too large to be transported by road, four of ITER’s six poloidal field coils, 8 to 24 m in diametre) will be assembled by Europe in this 12,000 m² facility.
PF Coil winding facility

## Slide 11
Poloidal Field Coils Production
Cadarache: Production of the Double Pancakes is well underway for PF5 (6 wound, 2 impregnated, 2 preparing for impregnation). Installation of the Cold Test Facility in progress;
ASIPP (CN): Production of the Double Pancakes almost completed for PF6 (9 wound-all completed, 8 impregnated, the last one preparing for impregnation). Stacking of the DPs has started.
EU
PF6 – Stacking of DPs started in ASIPP
PF5 – DP7 impregnated in Cadarache

## Slide 12: Current Progress PF1 Coil
Upper layer winding of Double Pancake (DP) #7
Measured diagram of DP 07 flatness
DP 04 after Vacuum Pressure Impregnation
Conductor Termination Bending
Fabrication of PF-1 Double Pancakes on schedule
Diagram of radius measurement of DP 07
Radiographic test of DP06 welded helium inlet

## Slide 13: Progress of Vacuum Vessel (VV)
Poloidal Segment #2 (PS2): T-rib, Flexible Support Housing (FSH) and In-Wall Shielding Support Rib (IWS SR) Assembly
Poloidal Segment #3 (PS3): Completion of In-Wall Shielding Block Assembly
Poloidal Segment #4 (PS4): T-rib, FSH and IWS SR Assembly
  Manufacture of VV Sectors by HHI is ongoing in order to ensure First Plasma in December 2025, but with many technical challenges;
  Manufacturing progress of the first Sector #6 is 82.8% (end of Aug 2018). Sector 7 is 64%, Sector 8 is 42% and Sector 1 is 25%.

## Slide 14
Significant increase of manufacturing capacity involving seven European welding industries;
Manufacturing rate increasing steadily, but still below expectation for some sectors;
Status of segments manufacturing as of August 2018 [compared to March 2018].
Vacuum Vessel
EU
New cooperative approach, EU and KO DAs
With AMW and HHI industries meeting in Monfalcone, September 2018
VV Sector 5: | 61% | [58]
VV Sector 4: | 59% | [50]
VV Sector 3: | 53% | [26]
VV Sector 2: | 50% | [15]
VV Sector 9: | 46% | [11]
PS1 Intermodular keys and T-ribs preparation at ENSA (SP) for Electron Beam Welding at Probeam (GE)

## Slide 15
Manufactured in India, the 30 m x 30 m cryostat is being assembled and welded on site.
Cryostat Workshop (ITER Site)
Lower cylinder
Base section
Upper cylinder
Lid

## Slide 16: Building Construction and Assembly

## Slide 17: Overview of the ITER Worksite

## Slide 18
Tokamak Bdg.
Assembly Hall
Radiofrequency Heating
Cryostat Workshop
PF Coil Winding Facility
Diagnostics Bdg.
Cryoplant
400 kV Switchyard
Tritium Bdg.
Magnet Power Conversions Bdgs.
Bioshield
~ Machine axis
Service Bldg.
Cooling System
Worksite progress
4 October 2018

## Slide 19: Rapid Progress Is Being Made in Building Construction
View in Feb. 2015:
View in July 2018:

## Slide 20
The bioshield (left) is now finalized. The high-resistance concrete-and-steel structure (the “Crown”) that will support the combined mass of tokamak + cryostat (23 000 tonnes) is in the last stages of completion (right). Signed agreement has been reached with EU and their contractors with a firm commitment to deliver the tokamak building for assembly work in March 2020.
Tokamak Complex

## Slide 21
Assembly Building
Before integration into the machine, components will be prepared and assembled in this 6,000 m2, 60 m high building. The Assembly Hall is equipped with a double overhead travelling crane with a lifting capacity of 1,500 t. Load tests, both static and dynamic (1,875 – 1,650 t), were finalized in December 2017. To the right, the installation of the sub-assembly tool (SSAT-1) is nearly complete.

## Slide 22
Vacuum Vessel Mock-up and Welding Tools
Welding tools and procedures for the VV assembly are being tested on a real-size mock-up at ENSA, Spain
EU

## Slide 23: Challenges of Assembly
Revised construction strategy endorsed by ITER Council
  Allows more flexibility to deal with delivery timing
  Regulatory hold point in 2020
Significant integration issues for installation of services in the tokamak building

## Slide 24
TF Cryolines
Section A-A
T&C Cryolines
Section B-B
CS Cryoline
HVAC
Cable Trays
BusBar
CHWS
CCWS
Sequence of Installation: Top to Bottom
HVAC & Cable Trays  TB04 Contract
CCWS/CHWS  TCC1 Contract
T&C Cryolines MPL Contract
BusBar BusBar Contract
Sequence of Installation:
TF Cryolines MPL Contract
CS Cryolines MPL Contract
CCWS/CHWS  TCC1 Contract
HVAC TB04 Contract
BusBar BusBar Contract
Cables Trays TB04 Contract
BusBar
Co-Activities in Tokamak Complex - B2 Level NW Corner

## Slide 25: System Commissioning
Master system commissioning schedule developed and will continue to be refined
Progression of systems to be brought into service:
  Steady-state Electric (enters operation Jan. 2019)
  Coil power supply connection to French grid (Q1 2019)
  Demineralized water/compressed gases (starts 1st half 2019)
  Cooling water (starts 1st half 2019)
  Cryogenic plant (starts 1st half 2020—ITER Council milestone)
  Coil power supplies (end 2021)
  First ECH subsystems (end 2021)

## Slide 26: Electrical Network Being Commissioned
The connection of the 400 kV switchyard to the French grid was successfully established on 17-18 Sept. 2018. Full operations to supply site power now planned for January 2019.

## Slide 27: Cooling Water System Is Being Prepared for Operation

## Slide 28: Progress of Cooling Water System
Horizontal Pumps
Pipe Modules
Vertical Turbine Pump Motor
Chemical Dosing System
Component Cooling Water System (CCWS), Chilled Water System (CHWS), Heat Rejection System (HRS) Manufacturing and shipment progress
Spools 50%
Supports 60%
Equipment 70%
Electrical 50%
I&C 90%

## Slide 29
Nearly 25 tons of liquid helium at 4 K will circulate in the ITER installation during operation.
Cryogenic System Is Critical For Proper Operation

## Slide 30
Cryoplant Construction Progressing
The ITER Cryoplant will be the largest single platform cryo-facility in the world. It will distribute liquid helium to various machine components (superconducting magnets, thermal shield, cryopumps, etc.). Installation of 11 helium and nitrogen tanks is now complete.
The installation of helium compressor skids on concrete pads was completed earlier this year. They will supply the cold boxes with gaseous helium at 21.8 bars and eventually provide the necessary gas flow for the supercritical helium cooling needs of the Tokamak.

## Slide 31: Major Challenges for System Commissioning
Systems must operate for client services while still being extended in construction (e.g., cooling water)
Site networks (electrical, gas, waste water, fire protection, etc.) are not complete at first
Main control building is not available for installation until mid-2022

## Slide 32: Updated ITER Research Plan

## Slide 33
A “Staged Approach” to Full Operating Capacity
Extensive interactions among the ITER Organization and Domestic Agencies to finalize revised baseline schedule (2015-6)
  Schedule estimates through First Plasma (2025) up to DT operation (2035) consistent with Members’ budget and technical constraints
Required a new ITER Research Plan (completed in 2017)
PFPO-1
PFPO-2
FPO
FP/EO

## Slide 34
Release of ITER Research Plan as ITER Technical Report
Written by IO staff and experts from ITER Members’ fusion institutions and DAs; recommended to ITER Council by STAC
ITER Research Plan made publicly available as ITER Technical Report ITR-18-003 for first time since ITER Organization established
Intended to be a ‘living document’ by working with the fusion community on details of experimental plans to achieve project’s goals and to define the supporting R&D required

## Slide 35: Integrated/Engineering Commissioning
Three key phases are envisioned in this period of operations:
Integrated commissioning (2025)
  Basic plant systems, magnets (to half current), 1/3 EC heating system, magnetic diagnostics calibrated, basic controls functional, as demonstrated by …
First Plasma!
  100 kA, 100 ms is the milestone
Engineering Commissioning (1st half 2026)
  Tests of magnets to full current
  Measurements of |B| surfaces to locate the first wall properly, if suitable method is found

## Slide 36: First Pre-Fusion Power Operating Phase (PFPO-I)
Tokamak |  |  |  |  |  |  |  |  |  | 
Plant |  |  |  |  |  |  |  |  |  | 
H&CD |  |  |  |  |  |  |  |  |  | 
Control |  |  |  |  |  |  |  |  |  | 
Physics |  |  |  |  |  |  |  |  |  | 
100% of final configuration
Main deliverables:
Demonstration of basic shape control (diverted plasmas up to 7.5 MA)
Commissioning of wall protection systems
Commissioning and validation of disruption mitigation system
Commissioning of EC system (20 MW, >100 s)
Measure heat loads
Note: this is ‘pre-fusion power’ because the working gas is either hydrogen or helium for low neutron generation

## Slide 37: Disruption Physics and Mitigation
Disruption mitigation is needed early in PFPO-I
  Validity of scaling projections for the mitigation will be immediately known
Operation at full field will be done in PFPO-I specifically to test the scaling of runaway generation with B

## Slide 38
Disruption Mitigation
13 mm
20 mm
17 mm
28 mm
  Disruption mitigation scenarios must be found which mitigate thermal and EM loads but at the same time avoid runaway electrons
  Task Force formed to carry out design validation and engineering studies
  IO will be responsible for implementation

## Slide 39
Key R&D contribution is validation of control models being used to assess the PCS, for example:
  Shape control development
  Wall protection schemes--heat flux control
  Fueling control
  Termination scenarios under ITER relevant control constraints (control of li, H-L transition, density, ELMs, detachment)
Simultaneous integration of control schemes:
  Actuator sharing: e.g. NTM and current density profile control
  Study of the interaction between different control schemes (e.g. between density control and detachment control)
Operations/Plasma Control System

## Slide 40: Second Pre-Fusion Power Operating Phase (PFPO-2)
Tokamak |  |  |  |  |  |  |  |  |  | 
Plant |  |  |  |  |  |  |  |  |  | 
H&CD |  |  |  |  |  |  |  |  |  | 
Control |  |  |  |  |  |  |  |  |  | 
Physics |  |  |  |  |  |  |  |  |  | 
100% of final configuration
Main deliverables:
Operation at 15 MA
Validation of disruption mitigation system
Commissioning of full heating power to >100 s
Operation in H mode
Demonstration of heat flux control in the divertor

## Slide 41: Handling Heat and Particle Flux
Power load [MW/m2]
Rolls Royce Trent 900
Re-entry
vehicle
ITER transients
Ariane 5/
Vulcain 2
HWR
ITER steady-state
~1 <10 85 2000
Arc welding
The challenge is not small!
The consequences of failing to protect in-vessel components are big—components are actively cooled (water) and replacement time is months

## Slide 42
Options for long-pulse operation in PFPO-II phase developed:
  7.5 MA H-modes offers the possibility of very long pulses
Long Pulse Operation May Be Possible
Ip (MA)
Flattop duration (s)
Achievable flat top durations for varying pre-magnetization current
  Main limit to exploitation may be system commissioning time to long pulse operation: e.g. H&CD, fuelling, PCS etc.

## Slide 43: Fusion Power Operating Phases
Tokamak |  |  |  |  |  |  |  |  |  | 
Plant |  |  |  |  |  |  |  |  |  | 
H&CD |  |  |  |  |  |  |  |  |  | 
Control |  |  |  |  |  |  |  |  |  | 
Physics |  |  |  |  |  |  |  |  |  | 
100% of final configuration
Main deliverables:
Commission tritium plant; license facility
500 MW fusion power, Q=10, 300-500 s
Q=5 in-principle steady-state operation
Explore technology of tritium breeding

## Slide 44
Two-week cycle: 12 days experiments/2 days maintenance
Two-year campaign cycle (from FPO-1)  ~415 days of experiments
Incorporating RAMI analysis for availability and conservative approach to disruption mitigation/recovery  ~13 pulses/day in 2 shift operation
Estimate of Available Experimental Time

## Slide 45: ITER R&D Needs
From the ITER Research Plan, a list of R&D needs (mostly physics) is being compiled and classified into the following categories:
  1: Major impact on design or IRP
  2: Could modify design or IRP strategy significantly
  3: Leads to design or IRP optimization
Goal is to complete internal review and release to the Members’ fusion communities before the ITPA CC/IEA CTP discussions in January 2019

## Slide 46: Preliminary Category 1 R&D Needs
Topics presently under discussion as category 1:
DMS
  Shard size, impurity composition for runaway avoidance (PFPO-I)
  Runaway dissipation (PFPO-I)
  Multiple injection (PFPO-I)
  Multiple location (PFPO-I)
  Alternative delivery scheme to SPI (PFPO-I)
  Alternative to gas injection (PFPO-II)
Laser induced desorption of tritium (FPO)
Single crystal mirror testing (PFPO-I)
Helium H-mode characterization (PFPO-II)
Mixed H/He H-mode threshold (PFPO-II)
EC wall conditioning (PFPO-I)

## Slide 47: Strategic Directions
ITER strongly supports (requires?) thriving domestic fusion programs in the Members:
  Conducting R&D in support of ITER operation
  Training staff for ITER operation and research
  Preparing the Member fusion communities to digest ITER results for the next steps toward fusion energy
ITER will only ‘succeed’ if there is something following ITER on a path to fusion energy
  Significant investments in technology required for fusion are needed to anticipate any potential next step

## Slide 48
Challenges Ahead Until Construction Completion
ITER Organization, Domestic Agencies and suppliers working as a team with a strong project culture
Strict respect by suppliers for quality and safety requirements
Strict respect by all stakeholders for the schedule requirements, in particular for the required delivery dates for materials and equipment on the ITER site
Reliable and fully integrated assembly/construction sequences on ITER site
Contracting with high-performing and experienced companies for the assembly activities in the Tokamak Complex
Setting in place a well-suited organization in charge of commissioning
Setting in place a well-suited organization to conceive and execute the progressive take-over of the machine, ultimately for its operation and maintenance
Timely, reliable availability of the planned and committed resources from the seven ITER Members

## Slide 49: ITER Will Be The First Look At Burning Plasma